Aims of the Accessibility Plan

This plan outlines how Carr Mill Primary School aims to increase access to education for pupils with disabilities in the three areas required by the planning duties in the Equality Act 2010 (i.e. the curriculum, physical environment and information).

A person is regarded as having a disability under the Act where they have a physical or mental impairment that has a substantial and long-term adverse effect on their ability to carry out normal day-to-day activities.

This plan aims to:

• Increase the extent to which pupils with disabilities can participate in the curriculum.

• Improve the physical environment of the school to enable pupils with disabilities to take better advantage of education, benefits, facilities and services provided.

• Improve the availability of accessible information to pupils with disabilities.

The above aims will be delivered within a reasonable timeframe, and in ways which are determined after taking into account pupils’ disabilities and the views of parents and pupils. In the preparation of an accessibility strategy, the LA must have regard to the need to allocate adequate resources in the implementation of this strategy.

The governing board also recognises its responsibilities towards employees with disabilities and will:

• Monitor recruitment procedures to ensure that individuals with disabilities are provided with equal opportunities.

• Provide appropriate support and provision for employees with disabilities to ensure that they can carry out their work effectively without barriers.

• Undertake reasonable adjustments to enable staff to access the workplace.

The plan will be resourced, implemented, reviewed and revised in consultation with:

• Pupils’ parents.

• The SLT and other relevant members of staff.

• Governors.

• External partners.

This plan is reviewed every three years to take into account the changing needs of the school and its pupils. The plan is also reviewed where the school has undergone a refurbishment.

The Accessibility Audit

The governing board will undertake an annual Accessibility Audit. The audit will cover the following three areas:

• Access to the curriculum – the governing board will assess the extent to which pupils with disabilities can access the curriculum on an equal basis with their peers.

• Access to the physical environment – the governing board will assess the extent to which pupils with disabilities can access the physical environment on an equal basis with their peers.

• Access to information – the governing board will assess the extent to which pupils with disabilities can access information on an equal basis with their peers.

When conducting the audit, the governing board will consider all kinds of disabilities and impairments, including, but not limited to, the following: • Ambulatory disabilities – this includes pupils who use a wheelchair or mobility aid

• Dexterity disabilities – this includes those whose everyday manual handling of objects and fixtures may be impaired

• Visual disabilities – this includes those with visual impairments and sensitivities

• Auditory disabilities – this includes those with hearing impairments and sensitivities

• Comprehension – this includes hidden disabilities, such as autism and dyslexia

The findings from the audit will be used to identify short-, medium- and long-term actions to address specific gaps and improve access.

All actions will be carried out in a reasonable timeframe, and after taking into account pupils’ disabilities and the preferences of their parents. The actions that will be undertaken are detailed in the following sections of this document.

Planning duty 1: Curriculum

|  | Issue | What | Who | When | Outcome | Review |
| --- | --- | --- | --- | --- | --- | --- |
| Short term | Staff members need continued CPD to ensure the curriculum can be adapted for individual pupils | Guidance from external agencies Additional CPD if required | SLT, teachers, SENCO | Ongoing dependent upon arising needs. | All children will be able to access the full school curriculum through planned and considered adaptation | Ongoing at individual pupil planned reviews |
| Medium term | The revised curriculum requires completion of the 2-year cycle so that any accessibility issues can be identified and addressed | Subject leader review following each curriculum cycle, coordinated by the DHT – Quality of Education | Teachers, SENCO, DHT - QE | End of the Summer Term 2023 | All pupils regardless of the individual needs will be able to access the full school curriculum | Summer 2023 |
| Long term | Continue to explore further enhancements to the curriculum to aid the experience for SEND pupils | Explore, via external professionals ICT adjustments for pupils with SEND | SLT, Computing Lead, SENCO | Summer 2022 | Improvement to the accessibility of learning | Summer 2025 |

Planning duty 2: Physical Environment

|  | Issue | What | Who | When | Outcome | Review |
| --- | --- | --- | --- | --- | --- | --- |
| Short term | Many pupils within the school require the implementation of sensory plans – resulting in a lack of space/time to do this. | Resourcing of then introduction of a morning Ready Get Set Sensory Club in the school hall for targeted pupils. | SENCo Trained LSAs | Autumn 2022 | A greater number of pupils will be able to have their sensory needs met daily. | Spring 2023 |
| Medium term | Several pupils are presenting with a level of sensory need, requiring a soothing environment with the school setting. | Conversion of the EYFS office space to provide a sensory room. | H/T SENCo EYFS Lead | Autumn 2022 | The new facility will enhance the provision of sensory support within school. | Summer 2023 |
| Long term | Improving the environment of the school to increase the extent to which disabled pupils can take advantage of education and associated services | Additional Signs: As required around the school to fulfil the need to direct visually impaired children and adults to parts of the school. | H/T Premises and P& I Committee | Spring 2023 | Signage will be in place. There will be easier access around school for the visually impaired | Summer 2023 |

Planning duty 3: Information

|  | Issue | What | Who | When | Outcome | Review |
| --- | --- | --- | --- | --- | --- | --- |
| Short term | A need to upskills the LSA staff team in understanding how to scaffold learning for SEND pupils without developing an over reliance upon adult support, | Training - Scaffolding learning for SEND pupils when writing. | All LSA | Network INSET day 31/10/22 | LSA Team will adopt a greater number of strategies when scaffolding learning – improving outcomes in writing. | Spring 2023 |
| Medium term | Teachers to improve their understanding of how to facilitate small steps of progress for pupils with SEND. | Introduction of the B-Squared assessment tool to be used to information teaching, learning and assessment. | DHT – P&I SENCo Teachers | Autumn 2022 | Small steps of progress will be tracked and used to inform next learning steps | Summer 2023 |
| Long term | The quality of transition for pupils with SEND can fluctuate to a discrepancies in how information is passed between educational setting. | St Helens Local Authority priority area for improvement Dave Harris Training | DHT – P&I SENCo | Commencing Autumn 22 |  | Spring 2024 |